## Gantt Chart
GANTT CHART | [5 empty] | Smartsheet Tip ➜ | [5 empty] | There are no tips.
PROJECT TITLE |  | College Enrollment System (CES) |  |  |  | COMPANY NAME | [6 empty] | Group 6
PROJECT MANAGER |  | Bach Ngo |  |  |  | DATE | [6 empty] | 2024-10-02
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE | [19 empty] | PHASE TWO | [19 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Phase 1 - SRS Document
1.1 | Section 1 | Janelle | 2024-09-05 | 2024-09-30 | 100% | bar: WEEK 3 M
1.2 | Section 2 | Roy | 2024-09-05 | 2024-09-30 | 100% | bar: WEEK 3 M; WEEK 3 F
1.3 | Section 3 - Functional Requirements | Bach & Roy | 2024-09-05 | 2024-09-30 | 100% | bar: WEEK 3 M to WEEK 3 F
1.4 | Section 4 - Non-Functional Requirements | Anthony | 2024-09-05 | 2024-09-30 | 100% | bar: WEEK 3 R to WEEK 3 F
1.5 | Section 5 - Diagrams | Anthony & Bach | 2024-09-05 | 2024-09-30 | 100% | bar: WEEK 3 F to WEEK 4 T
1.6 | Section 6 - Use Case Specifications | Janelle & Roy | 2024-09-05 | 2024-10-02 | 100% | bar: WEEK 3 F to WEEK 4 T
1.7 | Section 7 & 8 - Meeting Mins & Timeline | Janelle & Bach | 2024-09-05 | 2024-10-02 | 100% | bar: WEEK 4 W
2 | Phase 2 - ???
2.1 | ??? | ??? | 2024-10-03 | 2024-10-30 | 0%
2.2 | ??? | ??? | 2024-10-03 | 2024-10-30 | 0%
2.3 | ??? | ??? | 2024-10-03 | 2024-10-30 | 0%
2.4 | ??? | ??? | 2024-10-03 | 2024-10-30 | 0%
3 | Final Phase - ???
3.1 | ??? | ??? | 2024-10-31 | 2024-12-02 | 0%
3.2 | ??? | ??? | 2024-10-31 | 2024-12-02 | 0%
3.3 | ??? | ??? | 2024-10-31 | 2024-12-02 | 0%
3.4 | ??? | ??? | 2024-10-31 | 2024-12-02 | 0%